## Predicted
GANTT CHART
PRODUCT | AutoFarmOS | [10 empty] | DEVELOPMENT TEAM | [9 empty] | Team #7
PRODUCT OWNER | TerraFarm | [10 empty] | VERSION DATE | [9 empty] | 2019-10-28
FALL 2019
TASK | DURATION (DAYS) | SEPTEMBER | [7 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
|  | WEEK 1 | [5 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Project Definition and Planning
Define project specifications | 28 | bar: WEEK 1 23 to WEEK 4 18
Research/Select sensors | 10 | bar: WEEK 4 13 to WEEK 5 22
Research/Select OS and CPU Mem Board | 10 | bar: WEEK 4 13 to WEEK 5 22
Define project integration with product | 8 | bar: WEEK 5 21 to WEEK 6 28
Order/Obtain required tools | 8 | bar: WEEK 5 21 to WEEK 6 1
Define software architecture | 14 | bar: WEEK 6 27 to WEEK 7 9
Prototype Development
Setup hardware for development | 7 | bar: WEEK 6 2 to WEEK 7 8
Research hardware/software connectivity | 7 | bar: WEEK 7 5 to WEEK 8 11
Write drivers for sensors | 21 | bar: WEEK 8 12 to WEEK 11 2
Write tests for drivers | 14 | bar: WEEK 10 26 to WEEK 12 9
Debugging | 21 | bar: WEEK 10 26 to WEEK 13 16
Present Prototype to Product Owner | 5 | bar: WEEK 13 17 to WEEK 13 21
SPRING 2020
TASK | DURATION (DAYS) | WEEK 1 23: JANUARY; WEEK 2 4: FEBRUARY; WEEK 6 2: MARCH; WEEK 11 3: APRIL
|  | WEEK 14 |  |  |  |  | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Product Development
Make adjustments requested by Product Owner | 12 | bar: WEEK 14 21 to WEEK 15 1
Add API wrappers | 21 | bar: WEEK 16 2 to WEEK 18 22
Write tests for API wrappers | 14 | bar: WEEK 18 16 to WEEK 19 29
Write system tests | 28 | bar: WEEK 20 1 to WEEK 23 28
Debugging | 42 | bar: WEEK 18 16 to WEEK 23 28
Present Final Product to Product Owner | 7 | bar: WEEK 24 29 to WEEK 24 4
Product Finalization
Make adjustments requested by Product Owner | 7 | bar: WEEK 25 5 to WEEK 25 11
Ensure interfacing functionality | 14 | bar: WEEK 25 5 to WEEK 26 18
Debugging | 14 | bar: WEEK 25 5 to WEEK 26 18