## Predicted
GANTT CHART
PRODUCT | AutoFarmOS | [10 empty] | DEVELOPMENT TEAM | [9 empty] | Team #7
PRODUCT OWNER | TerraFarm | [10 empty] | VERSION DATE | [9 empty] | 2020-02-10
FALL 2019
TASK | DURATION (DAYS) | SEPTEMBER | [7 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER
|  | WEEK 1 | [5 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13
|  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Project Definition and Planning
Define project specifications | 27 | bar: WEEK 1 23 to WEEK 4 18
Research/Select sensors | 14 | bar: WEEK 4 13 to WEEK 5 26
Research/Select OS and CPU Mem Board | 14 | bar: WEEK 4 13 to WEEK 5 26
Define project integration with product | 8 | bar: WEEK 5 21 to WEEK 6 28
Order required tools | 12 | bar: WEEK 5 21 to WEEK 6 1
Research software needs/tools | 14 | bar: WEEK 6 27 to WEEK 7 9
Product Development Preparation
Await hardware order | 19 | bar: WEEK 8 10 to WEEK 10 28
Setup hardware for development | 15 | bar: WEEK 10 29 to WEEK 12 13
Research hardware/software connectivity | 15 | bar: WEEK 11 7 to WEEK 13 21
SPRING 2020
TASK | DURATION (DAYS) | WEEK 1 23: JANUARY; WEEK 2 4: FEBRUARY; WEEK 6 2: MARCH; WEEK 11 3: APRIL
|  | WEEK 14 |  |  |  |  | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18 | [6 empty] | WEEK 19 | [6 empty] | WEEK 20 | [6 empty] | WEEK 21 | [6 empty] | WEEK 22 | [6 empty] | WEEK 23 | [6 empty] | WEEK 24 | [6 empty] | WEEK 25 | [6 empty] | WEEK 26
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Product Development
Setup development environment | 20 | bar: WEEK 14 21 to WEEK 16 8
Write/obtain drivers for sensors and actuators | 14 | bar: WEEK 17 9 to WEEK 18 22
Write tests for drivers | 12 | bar: WEEK 18 16 to WEEK 19 27
Debugging | 28 | bar: WEEK 17 9 to WEEK 20 7
Add API wrappers | 14 | bar: WEEK 20 1 to WEEK 21 14
Write tests for API wrappers | 14 | bar: WEEK 21 8 to WEEK 22 21
Write system tests | 14 | bar: WEEK 21 8 to WEEK 22 21
Debugging | 24 | bar: WEEK 20 1 to WEEK 23 24
Present Final Product to Product Owner | 7 | bar: WEEK 23 22 to WEEK 23 24
Product Finalization
Make adjustments requested by Product Owner | 7 | bar: WEEK 23 25 to WEEK 24 31
Ensure interfacing functionality | 14 | bar: WEEK 23 25 to WEEK 25 7
Debugging | 18 | bar: WEEK 23 25 to WEEK 25 11